## Лист1
Country | Components | Main achievements in 2019 | Main achievements for the project
Afghanistan | Component 1 Capacity development and academic exchanges | Five (5) Afghan MS students newly admitted and enrolled with ultimate graduation set for 2021 | Afghan students are now part of the regional educational program on IWRM in the Kazakh-German University. All the students are nominated from the governmental structures, and this opportunity helps them building networks with their colleagues from other CA countries. Eight (8) MS students admitted since project start including 3 who have successful graduated by now.
| Component 2 Networking and cooperation | Afghanistan initiated the process of signing an MoU with the TIIAME in order to learn more on the structure and educational programs of young generation as well as the programs on re-training of the governmental specialists in water resources management. This will be used in establishment of the similar University in Afghanistan under the Ministry of Energy and Water Five (5) young Afghan leaders successfully upgraded their leadership skills and got networked with their regional counterparts under 10th CALP | Afghan Universities are now is a part of Network of Academic Communities of Central Asian countries 19 Afghan leaders successfully upgraded their leadership skills and got networked with their regional counterparts under 4 CALPs since start.
| Component 3 IWRM promotion and support | The Ministry of Energy and Water received expert support in designing an information-exchange and data-collection model for use by national WRM entities; The expert hired for this task was also part of the expert group that developed addendum to the current water law, which was approved by the Government in fall 2019 A 10-member delegation from MEW, MAIL and MoFA visited Uzbekistan for major lessons learning on managing dams, capacity building for water professionals and WRM in general Six (6) trainings conducted on various priority topics of interest to national partners and stakeholders to support water sector reforms (attended by 128 people) | The SWP provided hardware support to Afghanistan (fitting the conference room at Kabul Polytechnic University) The project staff developed the mandate for the basin councils operation, which will be used for all other basin councils in Afghanistan A comprehensive Situational Analysis Study completed for the Lower Harirud river basin as an example to follow in the other rivers of Afghanistan
| Component 4 Basin planning | The Small Basin Council for the Lower Harirud River was finally established in Afghanistan. This is the first basin council in the country officially recognized by the Ministry of Energy and Water. The basin plan for the Lower Harirud is currently in the making to soon emerge as the first basin management plan in the country. | A comprehensive Situational Analysis Study completed for the Lower Harirud river basin as the basis to develop a Basin Plan.
Kazakhstan | Component 1 Capacity development and academic exchanges | Two (2) Kazakh MS students admitted and enrolled in 2019 with ultimate graduation set for 2021 | Six (6) MS students from KZ admitted at DKU since project start of which 2 have successful graduated by now.
Component 2 Networking and cooperation
| Component 3 IWRM promotion and support | In Kazakhstan, the educational reform in the water sector was supported in cooperation with the Kazakhstan office of the Executive Directorate of the International Fund for Saving the Aral Sea (ED IFAS). 2 professional standards were updated and now are used by domestic universities to develop their own academic programs, and by employers – to assess the qualifications of potential employees; | The project provided the MIKE 11 software to the Kazhydromet along with the trainings for its staff. The software will allow forecasting the flood events for the major river basins in Kazakhstan to and take precautionary measures to minimize losses from the floods. An International Water Law training workshop by a first-class international practitioner conducted for key national partners and stakeholders in Kazakhstan (40 people trained incl. 15 females)
| Component 4 Basin planning | A basin plan for Kurkureu river fully finalized and started implemented The older basin plan for Aspara river newly updated and consolidated for implementation The first joint celebration of the Aspara river day took place in July 2019.The first joint celebration of the Kurkureu Suu river day took place in October 2019. | 15 SBC meetings held at 2 project rivers of which 11 were joint SBC meetings with co-riparians from KG Two priority needs from the Aspara Basin Plan supported and implemented: a new mobile op-con facility launched; the course of the river cleaned for better flow 3 River days celebrated as a proven water cooperation and trust building approach between shared river watersheds at two rivers between Kazakhstan and Kyrgyzstan (Aspara and Kurkureu)
Kyrgyzstan | Component 1 Capacity development and academic exchanges | Five (5) Kyrghyz MS students admitted and enrolled in 2019 with ultimate graduation set for 2021 | Nine (9) MS students admitted since project start including 3 to have successfully graduated by now and 1 to have dropped.
Component 2 Networking and cooperation
| Component 3 IWRM promotion and support | The Government approved the project-supported addendum to the Law on Water and the Water Code aimed at laying the foundation for introducing and deploying economic water use incentives across the country; The project continued its support to developing a unified hydrological glossary for the country to be used by all national authorities in law-making, documents and educational programs. | The project supports development of a unified hydrological glossary for the country to be used by all national authorities in law-making, documents and educational programs. An International Water Law training workshop by a first-class international practitioner conducted for key national partners and stakeholders in KG (70 people trained incl. 38 females)
| Component 4 Basin planning | Overall, in 2019 the Kyrgyz SBCs at 5 project rivers have held 6 one-sided meetings, 4 joint SBC meetings and 5 river days of which 3 were conducted in Kyrgyzstan | Five (5) Kyrghyz SBCs established at 5 transboundary rivers shared with 3 CA countries – KZ, TJ and UZ The project signed the MoU with the World Bank project, dealing with basin planning on the major river basins in the country. Based on this MoU, the World Bank’ project will use the Basin Planning methodology, promoting through the Smart Waters on all basins in the country. In overall, 33 SBC meetings held at 5 project rivers of which 17 were joint SBC meetings with co-riparians from 3 neighbor countries - KZ, TJ and UZ. These were complemented by 9 training workshops on various topics from basin planning to those locally demanded Two basin plan pilots supported and fully implemented by now: a new mobile op-con facility launched at Aspara along with the course of the river mechanically cleaned to improve the flow. 7 River days celebrated jointly with co-riaprians as a proven water cooperation and trust building approach at four rivers shared with KZ, TJ and UZ (Aspara, Kurkureu, Isfara and Padysha-Ata). Of thes 4 river days were conducted in Kyrgyzstan
Tajikistan | Component 1 Capacity development and academic exchanges | Three (3) Tajik MS students newly admitted and enrolled with ultimate graduation set for 2021 | Eight (8) MS students admitted since project start including 4 who have successful graduated by now.
Component 2 Networking and cooperation
| Component 3 IWRM promotion and support | In Tajikistan the new Law on Irrigation and Reclamation was developed and under the process of final comments from the concerned governmental agencies. By now, 17 out of 18 ministries provided their comments. After receiving the last comments from the Ministry of Energy and Water, the draft law will be submitted to the Government for final approval. | An International Water Law training workshop by a first-class international practitioner conducted for key national partners and stakeholders in TJ (102 people trained incl. 32 females)
Component 4 Basin planning
Turkmenistan | Component 1 Capacity development and academic exchanges | Six (6) Turkmen MS students newly admitted and enrolled with ultimate graduation set for 2021 7 webinars for Turkmenistan water professionals facilitated by TIIAME and KPU faculty. More webinars are planned for next year, inter alia with the involvement of KPU, DKU and State Enterprise (SE) TajikNIIGiM. | Four (4) MS student candidates admitted as guest students for a preparatory course before allowed for admission exams.
Component 2 Networking and cooperation
| Component 3 IWRM promotion and support | The Provisions for the operation of basin councils and basin organizations were drafted to facilitate the enforcement of the country’s new Water Code; | Turkmenistan (establishing 2 Information-Training Classes). A series of International Water Law training workshops by a first-class international practitioner conducted for key national partners and stakeholders in TJ (almost 200 people trained incl. 65 females)
| Component 4 Basin planning | 2 SBC meetings and 1 region-wide SBC Forum were held in 2019 in TM | 1 Small Basin Council for the Murgab river basin was established which is the first and only basin council in Turkmenistan. Overall, 4 SBC meetings and 1 SBC Forum were held in TM. These were complemented by 3 training workshops mostly on SBC establishment and basin planning
Uzbekistan | Component 1 Capacity development and academic exchanges | The 2nd Summer School took place in TIIAME for the MA students of DKU and TIIAME, which helps making more networking with the Uzbek Students. | Overall, there were 2 summer schools in TIIAME supported by the project. 7 students from TIIAME and 24 students from DKU participated in the course.
| Component 2 Networking and cooperation |  | During the project period, thanks to the Network of Academic Communities meetings, the 3 MoUs were signed by TIIAME with TajikNIIGiM, Tajik Agrarian University and Kabul Polytechnic University.
| Component 3 IWRM promotion and support | The development of Procedures for Water Use and Consumption Accounting, Reporting and Monitoring and the Order on the Development of Hydro-Technical Facility Safety Declaration is in progress. | An International Water Law training workshop by a first-class international practitioner conducted for key national partners and stakeholders in UZ (68 people trained incl. 21 females)
| Component 4 Basin planning | 4 SBC one-side meetings, 1 joint SBC meeting, 1 River Day A room for SBC to seat, meet and work was furnished and computer equipped. | The Padshaata Small Basin Council is the first small basin council in the country. There are 3 more working groups on basin planning (including the one on the Yomonjar canal), but the Ministry of Water does not consider them as a basin council. 7 SBC one-sided meetings, 2 study tours, 2 joint SBC meetings, 1 River Day
Regional cooperation | Component 1 Capacity development and academic exchanges | 6 more students graduated from their 2-year IWRM MA studies at Kazakh-German University In 2019, the SWP sponsored 21 students to get their MAs in IWRM from DKU. Overall for the 4 years, the project provided scholarships to 26 students from CA countries and Afghanistan. A total of 1,800 people increased their knowledge on WRM, water diplomacy, water-efficient technologies and international water law by participating in 62 capacity-building events, including 7 in Turkmenistan in a completely new format – webinars – ensuring an even stronger academia reconnect and involving more participants at low cost; | During Year 4 the project has held over 200 events across all levels and components. 80% of all the activities were at national and local levels (40% each), while the remaining 20% were regional events. The total number of people to have attended all this amounted to over 3400, of which women comprised 23%.
| Component 2 Networking and cooperation | Additional 24 young scientists received grants to implement their WRM-related field research projects; 5 representatives of governmental and non-governmental sectors from Afghanistan participated in CAREC’s annual Central Asian Leadership Program in 2019; 14 master students from TIIAME and DKU participated in the 2019 Summer School (Tashkent) to expand their expertise and competencies on water resources engineering;
| Component 3 IWRM promotion and support |  | The project supported all 6 countries in promoting water sector reforms. Different expert works were sponsored on development of the new laws, bylaws, standards and provisions, as well as development of the information-exchange systems to help countries improving their daily management of water resource.
| Component 4 Basin planning |  | The basin planning methodology is being promoted through the project and is recognized by the national partners. This methodology is now applied in Kyrgyzstan for development of 5 national basin plans. The methodology is also interesting for Afghanistan, and the National Procurement Agency of Afghanistan is planning to use it for prioritization of the needed infrastructural support for the 5 main basins in the country.